## Sheet1
NATIONAL EVENT TASK LIST
Event Name
Event Location
Event Date
Event Roles to be filled | Name | Email Address | Phone Number | Comments
Event Manager
Race Director
Registration Staff
Volunteer Coordinator
Village Coordinator
Medical Coordinator
Event Announcer
PCP Commissiare
Commissaire 1
Commissaire 2
Commissaire 3
Commissaire 4
Photographer
Insert other roles as required
Event Preparation | Detail | Responsibility | Due | Comments
Host Guidelines | Develop host guidelines for National Cup/Series | AusCycling | When EOIs open
Host Funding | Funding application for Local/State Government grants | AusCycling/Host | 6 months prior
Host Agreeement | Formal agreement/MOU between parties | AusCycling | 3 months prior
Hosting Fee | Payment required as per agreement | AusCycling/Host | As per agreement
Land Permit Approvals | Dependent on landowner deadlines | Host | 3 months prior
Private Promoters Application (if applicable) | Submit application for private promoter insurance https://auscycling.org.au/page/eventorganisers | Host | 2 months prior
Draft Schedule |  | Host | 2 months prior
Course Map | GPS track file, profile, length, feedzones | Host | 2 months prior
Entry Fees | Set entry fees for event and any support events being conducted | Host | 2 months prior
Open Entries |  | Host | 2 months prior
Event Management Plan (EMP) | MTB template available - https://auscycling.org.au/page/resources | Host | 6 weeks prior
Risk Management Plan (RMP) | MTB template available - https://auscycling.org.au/page/resources | Host | 6 weeks prior however monitor ongoing
Traffic Management Plan | Emergency access and road closures (included in EMP template) | Host | 6 weeks prior
Medical Map | Location of medical services on course and in village (included in EMP template) | Host | 6 weeks prior
Marshall Map/Plan | Estimated location of course marshalls and quantity | Host | 6 weeks prior
Weather Contingency Plan | What are major issues that major arise & contingency plan (included in EMP template) | Host | 6 weeks prior
Insurance (Certificate of Currency) | Advise of interested parties to be listed on COC | Host | 6 weeks prior
Volunteer Registration | Set up volunteer registration system | Host | 6 weeks prior
Signage (Directional, Village) | AusCycling Technical Delegate to assist | AusCycling/Host | 4 weeks prior
Podium Backdrop (If applicable) |  | Host/Auscycling | 4 weeks prior
Podium Prizes | Medals provided by AC for National & State Championships. Hosts may purchase for other events | Host | 4 weeks prior
VIP Guest for Presentation | Invitations to VIPs/Sponsors | Host | 4 weeks prior
Finalise event schedule |  | Host | 4 weeks prior
Village Map (Including Parking) | Map showing village services, amenities. Include emergency evacuation points | Host | 2 weeks prior
DHI Transport Plan (if applicable) | Number of shuttles, capacity and trailers | Host | 2 weeks prior
Race Plates |  | Host | 2 weeks prior
Event Run Sheets |  | Host | 2 weeks prior
Finalise workforce roster |  | Host | 1 week prior
Contractors to be engaged | Detail | Responsibility | Due | Comments
Timing | Minimum specs as per 'National Event Specification Standard' - available in website resources | Host | 6 weeks prior
Medical/First Aid | As per guidelines in Organisers Guide | Host | 6 weeks prior
Catering | Variety of food options suitable for the number of competitors. Promote prior to event | Host | 6 weeks prior
Coffee Operator |  | Host | 6 weeks prior
Radio/Communication | Minimum specs as per 'National Event Specification Standard' - available in website resources | Host | 6 weeks prior
PA/Music System | Minimum specs as per 'National Event Specification Standard' - available in website resources | Host | 6 weeks prior
Shuttle Service (If required) | Capacity, trailer configuration | Host | 6 weeks prior
Fencing | Crowd control fencing for start, finish locations and other key locations | Host | 6 weeks prior
Toilets | As per guidelines in Organisers Guide | Host | 6 weeks prior
Waste Management | As per guidelines in Organisers Guide | Host | 6 weeks prior
Security | Overnight security for asset protection if required | Host | 6 weeks prior
Lighting (If required) | Consideration for events running into evening and asset protection. | Host | 6 weeks prior
Website & Social Media Content | Detail | Responsibility | Due | Comments
Calendar Listing |  | AusCycling | Once confirmed
Event Logos | National Cup logos to be used in event promotion | AusCycling | Once confirmed
Course Description | 50 - 100 word description for event page | Host | 3 months prior
Venue Address | Venue address and travel desription | Host | 3 months prior
Entry Link |  | Host | 2 months prior
Event Webpage | Links to Event website (if in addition to AusCycling event page) | Host | 2 months prior
Event Facebook page | Link to Event Facebook page | Host | 2 months prior
Direction Map | If applicable | Host | 4 weeks prior
Final Event Schedule | Event timings including support events | Host | 2 weeks prior
Timing Link |  | Host | 2 weeks prior
Sponsors | Details of any local sponsors and logos (if applicable) | Host | Ongoing
Local Promotion Links | Local accommodation and services (if applicable) | Host | Ongoing
EDM Content | Content for event promotion | Host | Ongoing
Use of Official Hashtags |  | Host/Auscycling | Ongoing
EVENT BUILD & OPERATIONS
Course Build | Detail | Responsibility | Due | Comments
Signage | Marshall points, Km to go, arrow, caution, etc | Host | 4 weeks prior
Bunting | Supply of bunting, calculation of what will be required | AusCycling/Host | 4 weeks prior
Start/Finish Straight | As per Tech Regs. | Host | 4 weeks prior
Feed Zone | Location/Size of feed zone - as per Tech Regs | Host | 4 weeks prior
Equipment | Club equipment available and onsite | Host | 1 week prior
Village | Detail | Responsibility | Due | Comments
Registration | All weather space with power | Host | 2 weeks prior
Timing Tent/Location | Covered area for timing services, media and announcer (finish line location with power) | Host | 2 weeks prior
Presentation Area & Podium | Assign presentation area and podium produced (if applicable) | Host | 2 weeks prior
Expo/Team Tent Location | Location for exhibitors mapped out and team tent bookings | Host | 2 weeks prior
Medical Tent/Location | Covered area with privacy for medical team | Host | 2 weeks prior
Bike Wash | Water, power and location if required | Host | 2 weeks prior
Power/Water Supply | Services required in event village e.g. food vendors, PA, drinking water, bike wash | Host | 2 weeks prior
Table/Chairs | Seating for public and supporters | Host | 2 weeks prior
Infrastructure Bump-In | Toilets, fencing, generators, etc | Host | 1 -2 days prior
Volunteers | Detail | Responsibility | Due | Comments
Roster | Schedule volunteers to assist with course markings and post event clean-up | Host | 6 weeks prior
Village Helpers | General volunteers for parking, signage, waste management, amentities | Host | 2 weeks prior
Course Marshalls | Final roster - schedule and locations | Host | 2 weeks prior
Marshall Equipment | Vest, flags, whistles | Host | 2 weeks prior
Volunteers Catering | Supply of water, snacks and meals for volunteers | Host | 1 week prior
Timing Assistants | Volunteer to assist timing contractor (if required) | Host | 1 week prior
Site | Detail | Responsibility | Due | Comments
Infrastructure Bump-Out |  | Host | 1 day post-event
Bunting/Track Cleared |  | Host | End of event
Village Cleared |  | Host | 2 days post-event
Waste Removed |  | Host | 2 days post-event
Addition Comments/Queries